# Microsoft Project Teaching Path (Complete Instructor Guide)

## Overview

This teaching path is designed to help you deliver a structured, practical course on Microsoft Project from beginner to intermediate level. It includes lesson sequencing, hands-on exercises, and project-based learning.

# Module 1: Introduction to Project Management & MS Project Basics

## Objectives

- Understand what project management is

- Learn the role of Microsoft Project

- Explore the interface

## Topics

- What is a project?

- Project lifecycle

- Introduction to Microsoft Project

- Interface overview (Ribbon, Gantt Chart, Task Table)

## Activity

- Open MS Project

- Create a new blank project

- Explore views

## Exercise

Create a simple project titled:

“Office Renovation Project”

Add 5 sample tasks without dates.

# Module 2: Creating Tasks & Work Breakdown Structure (WBS)

## Objectives

- Build structured project tasks

- Understand WBS hierarchy

## Topics

- Tasks vs summary tasks

- Indentation and outdentation

- Task relationships

## Activity

- Build a WBS for a real project

## Exercise

Project: “Event Planning”

- Venue booking

- Catering

- Invitations

- Logistics

- Event execution

Make at least 3 levels of hierarchy.

# Module 3: Scheduling & Dependencies

## Objectives

- Understand task sequencing

- Use dependencies correctly

## Topics

- Finish-to-Start (FS)

- Start-to-Start (SS)

- Lag and Lead time

## Activity

- Link tasks using dependencies

## Exercise

Create a construction project schedule:

- Foundation

- Walls

- Roof

- Painting

Apply dependencies correctly.

# Module 4: Resources Management

## Objectives

- Assign resources to tasks

- Understand resource types

## Topics

- Work resources

- Material resources

- Cost resources

## Activity

- Create resource sheet

## Exercise

Assign:

- 2 workers

- 1 project manager

- 1 contractor

# Module 5: Cost Management

## Objectives

- Add and manage costs

## Topics

- Fixed costs

- Resource-based costs

## Activity

- Add costs to tasks

## Exercise

Add budget to “Event Planning” project

# Module 6: Baselines & Tracking Progress

## Objectives

- Save baseline

- Track project progress

## Topics

- Baseline definition

- % complete tracking

- Variance analysis

## Activity

- Set baseline

## Exercise

Update project progress after 3 simulated days

# Module 7: Reports & Views

## Objectives

- Generate reports

- Analyze project performance

## Topics

- Gantt Chart

- Timeline view

- Reports dashboard

## Activity

- Generate report

## Exercise

Create:

- Cost report

- Task progress report

# Module 8: Final Project (Capstone)

## Objective

Apply all learned skills

## Project

“Build a Small Office IT Setup Project”

## Requirements

- WBS structure

- Dependencies

- Resources

- Costs

- Baseline

- Progress tracking

## Deliverables

- Full MS Project file

- Exported PDF report

# Assessment Criteria

- Correct WBS structure (20%)

- Proper dependencies (20%)

- Resource allocation (15%)

- Cost accuracy (15%)

- Tracking & baseline usage (20%)

- Final presentation (10%)

# Teaching Tips

- Always demonstrate before letting students practice

- Use real-life examples (construction, events, IT)

- Encourage mistakes during scheduling (learning through correction)

- Repeat dependency logic until clear

# Optional Extension Module

- Critical Path Method (CPM)

- Earned Value Management (EVM)

- Advanced reporting

# Microsoft Project Training – PowerPoint Slide Deck Structure

## Slide Deck Overview

This deck is structured module-by-module so you can directly convert each section into PowerPoint slides.

# MODULE 1: Introduction to MS Project

## Slide 1: Title

Microsoft Project – Introduction

## Slide 2: What is Project Management?

- Definition of a project

- Why planning matters

## Slide 3: Role of MS Project

- Scheduling tool

- Tracking tool

- Resource management tool

## Slide 4: Interface Overview

- Ribbon

- Gantt Chart

- Task Table

## Slide 5: First Hands-on

- Create blank project

- Add sample tasks

# MODULE 2: Tasks & WBS

## Slide 1: What is WBS?

- Work Breakdown Structure definition

## Slide 2: Tasks Types

- Task

- Summary task

## Slide 3: Structuring Tasks

- Indent / Outdent

## Slide 4: Exercise

- Event Planning WBS

# MODULE 3: Scheduling & Dependencies

## Slide 1: Task Relationships

- FS, SS, FF, SF

## Slide 2: Dependency Logic

- Why sequencing matters

## Slide 3: Lag & Lead

## Slide 4: Exercise

- Construction project schedule

# MODULE 4: Resources

## Slide 1: Resource Types

- Work

- Material

- Cost

## Slide 2: Assigning Resources

## Slide 3: Resource Sheet Overview

## Slide 4: Exercise

- Assign team roles

# MODULE 5: Cost Management

## Slide 1: Cost Types

- Fixed cost

- Resource cost

## Slide 2: Budgeting in MS Project

## Slide 3: Exercise

- Event budget setup

# MODULE 6: Tracking & Baseline

## Slide 1: What is Baseline?

## Slide 2: Tracking Progress

## Slide 3: % Complete

## Slide 4: Variance

## Slide 5: Exercise

- Simulated progress update

# MODULE 7: Reports

## Slide 1: Reporting Tools

## Slide 2: Gantt Chart View

## Slide 3: Dashboard Reports

## Slide 4: Exercise

- Generate reports

# MODULE 8: Final Project

## Slide 1: Capstone Project

## Slide 2: Requirements

- WBS

- Dependencies

- Resources

- Costs

## Slide 3: Deliverables

- File + PDF

# END

# Microsoft Project – Student Workbook

## How to Use This Workbook

- Complete exercises in MS Project

- Save files after each module

- Compare with provided answers

# MODULE 1: Basics

## Exercise 1

Create a project named:

Office Setup Project

Add 5 tasks:

- Planning

- Design

- Procurement

- Installation

- Testing

## Answer

Correct structure:

- Simple task list (no dependencies required)

# MODULE 2: WBS

## Exercise

Create WBS for Event Planning:

- Venue

- Catering

- Invitations

- Setup

- Execution

Add at least 2 levels.

## Answer

- Event Planning (Summary Task)

  - Venue

  - Catering

  - Invitations

  - Setup

  - Execution

# MODULE 3: Dependencies

## Exercise

Sequence:

- Foundation

- Walls

- Roof

- Painting

## Answer

- Foundation → Walls → Roof → Painting (FS links)

# MODULE 4: Resources

## Exercise

Assign:

- Project Manager

- Developer

- Designer

## Answer

All resources assigned in Resource Sheet and linked to tasks

# MODULE 5: Cost

## Exercise

Add costs to Event Project

## Answer

- Fixed cost per task

- Resource-based costs assigned

# MODULE 6: Tracking

## Exercise

Set baseline and update % complete after 3 days

## Answer

- Baseline saved

- Progress updated manually

# MODULE 7: Reports

## Exercise

Generate:

- Cost report

- Task report

## Answer

Reports exported from Project → Reports tab

# FINAL NOTES

- Always save versions

- Use Gantt Chart for validation

# MS Project Case Study – Real Project Scenarios

## Overview

This document contains 3 complete case study templates for MS Project training.

# CASE STUDY 1: Construction Project (Office Building)

## Project Name

Office Building Construction

## WBS

- Site Preparation

- Foundation

- Structure

- Roofing

- Electrical

- Plumbing

- Finishing

## Dependencies

- Site Prep → Foundation → Structure → Roofing → Finishing

- Electrical and Plumbing run in parallel after Structure

## Resources

- Engineers

- Electricians

- Plumbers

- Contractors

## Costs

- Material cost per phase

- Labor cost per resource

## Milestones

- Foundation Complete

- Structure Complete

- Project Delivery

# CASE STUDY 2: IT Project (System Implementation)

## Project Name

ERP System Deployment

## WBS

- Requirements Gathering

- System Design

- Development

- Testing

- Deployment

- Training

## Dependencies

- Sequential phases from Requirements to Deployment

## Resources

- Business Analyst

- Developers

- Testers

- Trainers

## Costs

- Development cost per phase

## Milestones

- Design Approved

- System Go-Live

# CASE STUDY 3: Event Project (Corporate Event)

## Project Name

Annual Corporate Event

## WBS

- Planning

- Venue Booking

- Catering

- Marketing

- Execution

## Dependencies

- Planning → Booking → Execution

- Marketing overlaps with Planning

## Resources

- Event Manager

- Suppliers

- Marketing Team

## Costs

- Venue cost

- Catering cost

- Marketing budget

## Milestones

- Venue Confirmed

- Event Completed

# TEACHER NOTE

Use these case studies for:

- Group assignments

- Final exam practical

- Live demo exercises

# MS Project Trainer Demo Script (Step-by-Step)

## Purpose

This script helps instructors demonstrate MS Project live in class.

# DEMO 1: Creating a New Project

## Step 1

Open Microsoft Project

## Step 2

Click: New → Blank Project

## Step 3

Name project:

Office Setup Demo

## Step 4

Explain interface:

- Task table

- Gantt chart

# DEMO 2: Adding Tasks

## Step 1

Add tasks:

- Planning

- Design

- Execution

## Step 2

Explain task structure

# DEMO 3: Creating WBS

## Step 1

Add subtasks under Planning:

- Requirements

- Budget

## Step 2

Use Indent button

# DEMO 4: Adding Dependencies

## Step 1

Select tasks

## Step 2

Click Link Tasks

## Step 3

Explain FS relationship

# DEMO 5: Adding Resources

## Step 1

Go to Resource Sheet

## Step 2

Add:

- Project Manager

- Developer

## Step 3

Assign to tasks

# DEMO 6: Setting Baseline

## Step 1

Go to Project tab

## Step 2

Click Set Baseline

## Step 3

Explain importance

# DEMO 7: Tracking Progress

## Step 1

Update % complete

## Step 2

Show variance

# DEMO 8: Reports

## Step 1

Go to Reports

## Step 2

Generate Cost Report

# TEACHER TIP

- Always narrate actions while clicking

- Let students replicate immediately

# Microsoft Project Certification Exam

## Part A: Theory (40%)

### Q1

What is Microsoft Project used for?

### Q2

Define Work Breakdown Structure (WBS).

### Q3

What is a task dependency?

### Q4

List 3 types of resources in MS Project.

### Q5

What is a baseline?

### Q6

Explain Finish-to-Start relationship.

### Q7

What is the purpose of tracking progress?

## Part B: Multiple Choice Questions

### Q8

Which view is most used in MS Project?
A) Excel View
B) Gantt Chart
C) Slide View
D) Data View

### Q9

Which feature shows task relationships?
A) Reports
B) Links
C) Filters
D) Notes

### Q10

Baseline is used for:
A) Printing
B) Tracking progress
C) Designing UI
D) Emailing

## Part C: Practical Exam (60%)

### Task

Create a project:

“Small Office Setup”

### Requirements:

- Create WBS (minimum 3 levels)

- Add at least 6 tasks

- Set dependencies

- Add 3 resources

- Assign resources

- Set baseline

- Update progress (simulate 30%)

## Evaluation

- WBS structure (20%)

- Dependencies (15%)

- Resources (15%)

- Baseline usage (10%)

## Instructor Notes

- Allow 90 minutes

- Use real-time observation

- Grade file submission

Done — you now have a full training package for MS Project:

You currently have:

- 📊 PowerPoint slide structure per module

- 📘 Student workbook (with exercises + answers)

- 🏗️ Real-world case studies (Construction / IT / Event)

- 🎤 Trainer step-by-step demo script

- 🧪 Certification-style exam (theory + practical)

### If you want to level this up into a real professional course, I can next help you build:

- 🎬 Actual PowerPoint file (.pptx download)

- 🧑‍🏫 Trainer speaking notes (word-for-word script per slide)

- 🧑‍💻 MS Project sample files (.mpp templates students open)

- 🏆 Grading rubric + marking sheet (Excel)

- 🎓 Full certification badge system (Beginner → Advanced levels)

Just tell me:
 👉 “turn this into a real academy course” or “make it production-ready”